## Slide 1
PROJECT EXPLANATION & IMPLEMENTATION
Solar-Based RO Drinking Water Initiative
Implementation & Project Delivery Overview
10 Government Schools | Banaskatha District, Gujarat
DigiGaon Foundation
Solar energy
Safe water
Schools
Clean drinking water for school children
Notes: This deck explains the Solar-Based RO Drinking Water Initiative: what will be installed in 10 government schools in Banaskatha District, how it will be delivered on the ground, who is responsible, how it is monitored, and how it keeps working after handover.

## Slide 2
THE CONTEXT
Why This Project Is Needed
CHALLENGE ON THE GROUND
WHAT IT LEADS TO
Groundwater contamination
High TDS · Fluoride · Microbial contamination
Water unsafe to drink untreated
Fluoride exposure raises fluorosis risk
Dependence on untreated sources
Unsafe handpumps and untreated water in many schools
Waterborne disease risk
High incidence reported among school children
Inconsistent electricity supply
Power deficit in the region
Conventional RO cannot run reliably
Grid-dependent purification stops when power fails
Low awareness
Water safety and hygiene practices
Unsafe habits continue
Clean water alone is not enough without awareness
The project response: solar-powered RO purification that treats water on site, using renewable energy instead of unreliable grid power.
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
2
Notes: Walk left to right: each challenge on the ground and the consequence it creates for the school. The last row explains why a conventional grid-powered RO is not enough, and why this project uses solar power.

## Slide 3
THE PROJECT IN ONE VIEW
Project at a Glance
10
Government schools
~3,000
Students (approx.)
140
Teachers
55,000+
Community members in surrounding areas
Location: Banaskatha District, Gujarat
[School names: to be added once selection is finalised]
WHAT THE PROJECT INCLUDES
Solar-powered RO purification
Renewable Energy –Powered Water Facility
Hygiene & sanitation awareness
12-month maintenance & water-quality testing
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
3
Notes: Four numbers describe the reach: 10 government schools, around 3,000 students, 140 teachers and more than 55,000 people in the surrounding communities. The bottom row lists the four things the project delivers.

## Slide 4
THE PHYSICAL INTERVENTION
What Will Actually Be Installed
Solar panels
Battery / power system
RO purification
UV / filtration
Safe water storage
Water cooler
Students & school community
SYSTEM COMPONENTS
3.5 KW
Rooftop off-grid solar PV system
5 batteries
Battery storage at each site
Inverter
Inverter & stabilizer
250 LPH
Water purification system
RO + UV
With carbon & sediment filtration
Fittings
Storage, racking, wiring & plumbing
200–250 L
Solar-powered water cooler
× 10 schools
One Solar RO system + cooler per school
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
4
Notes: Top row: how the system works, from sunlight to a child drinking clean water. Bottom grid: the specified components. Only specifications stated in the project document are shown.

## Slide 5
HOW THE PROJECT IS DELIVERED
The Six-Step Implementation Journey
1
School Identification
Transparent selection using local data
2
Baseline & Water Assessment
Infrastructure, students & water quality recorded
3
Procurement & Planning
Equipment, vendors & site plans
4
Installation
Solar, RO & cooler installed and tested
5
Training & Awareness
Staff, caretakers & community
6
Monitoring, Maintenance & Handover
12-month support; ownership to schools
PREPARE
Month 1–2
BUILD & TRAIN
Month 2–3
OPERATE & SUSTAIN
Month 3–12
From planning to functioning water infrastructure — each step feeds the next.
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
5
Notes: This is the backbone of the project. Steps 1 to 3 prepare the ground, steps 4 and 5 put the system in place and train people to use it, and step 6 keeps it working through 12 months of support before full ownership rests with the school.

## Slide 6
STEPS 1 & 2
School Selection & Baseline Assessment
Step 1 · School Selection
Transparent selection
Local data collection
Community needs assessment
PRIORITY GIVEN TO SCHOOLS WITH
Highest student density
Poorest water quality
Community commitment to sustainability
Existing infrastructure (space, roof, plumbing)
Step 2 · Baseline Data Collected
School infrastructure status
Student strength / attendance
Water quality
Existing water source
SITE VISIT
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
6
Notes: Step 1 explains how schools are chosen: transparently, using local data and a community needs assessment, against four criteria. Step 2 records the starting point at each school, during site visits, so that later changes can be measured.

## Slide 7
STEPS 3 & 4
From Procurement to a Working System
INSTALLATION
TESTING
PLANNING & PROCUREMENT
Off-site preparation
1 Procurement
Equipment & materials sourced
2 Vendor coordination
Supply & installation aligned with vendors
ON-SITE INSTALLATION
At each of the 10 schools
3
Site preparation
Rooftop & location readied
4
Solar installation
Panels, battery & inverter
5
RO installation
Purifier, storage & cooler
6
Plumbing & electrical
Wiring, pipes & connections
7
System testing
Full system run & checked
8
Quality & safety check
Verified before use
Result: a tested, verified and functioning system at each school, ready for training and handover.
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
7
Notes: Left: what happens before anyone goes on site — sourcing equipment and aligning vendors. Right: the on-site sequence at each school, ending with testing and a quality and safety check before the system is used. The two frames on the right are for installation and testing photographs.

## Slide 8
STEP 5
Training & Community Awareness
TRAINING
Staff and local caretakers trained on the installed system: operation, upkeep and water safety.
WHO IS TRAINED
Teachers & school staff
Local personnel / caretakers
WHAT IS COVERED
RO operation & upkeep
Water safety practices
Hygiene & sanitation awareness
COMMUNITY LOOP
Awareness programmes in schools & communities
Feedback: surveys & group discussions
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
8
Notes: Once the system is installed, the people who will run it are trained: teachers, school staff and local caretakers. Awareness sessions cover water safety, hygiene and sanitation, and community feedback is collected. The photo frame is for an image of a training or awareness session.

## Slide 9
ROLES & RESPONSIBILITIES
Who Delivers the Project
Project Manager
Overall coordination, timelines, reporting & field visits
Technical Coordinator
Installation, vendors, testing, technical issues & handover
Water & Sanitation Program Officer
Water testing, hygiene awareness, training & maintenance coordination
Project Supervisor
School & community coordination, feedback, data collection & local issues
Admin & Finance Executive
Procurement, payments, records, financial documentation & compliance
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
9
Notes: One Project Manager holds overall coordination. Four roles report in: technical delivery, water and sanitation, field supervision with schools and communities, and administration and finance.

## Slide 10
WHEN IT HAPPENS
Project Timeline: Month 1 to Month 12
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
M11
M12
Preparation
Month 1–2
School selection · Baseline assessment · Stakeholder consultation · Procurement planning
Installation
Month 2–3
Solar RO installation · Staff training · Awareness activities
Initial Operations
Month 3–4
Monitoring · Troubleshooting · Impact assessment · Documentation · Optimization
Sustained Operations
Month 4–12
Regular maintenance · Impact evaluation · Community engagement
Evaluation
Milestones
Mid-term review
Final evaluation & impact report
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
10
Notes: Read the timeline top to bottom. Preparation happens in months 1 to 2, installation and training in months 2 to 3, initial operations in months 3 to 4, and sustained operations with regular maintenance run from month 4 to month 12. A mid-term review in month 6 and a final evaluation in month 12 measure progress and outcomes.

## Slide 11
HOW MONITORING WORKS
Actively Monitored, Not Installed and Forgotten
Continuous monitoring cycle
1
Baseline
2
Installation verification
3
Daily / weekly activity logs
4
Photo / video evidence
5
Functional & hygiene checklists
6
Monthly reports
7
Feedback
8
Mid-course correction
WHAT IS CHECKED ON THE GROUND
Field visits (PM & Tech. Coordinator)
Geo-tagged photos & videos per milestone
System functionality checks
Water quality checks
Surveys & focus group feedback
Dashboard issue flagging & resolution
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
11
Notes: Monitoring runs as a cycle. It starts from the baseline, verifies the installation, and then keeps going through activity logs, photo and video evidence, checklists, monthly reports and feedback. Any issue leads to corrective action, and the cycle repeats. The right panel lists what is physically checked on the ground.

## Slide 12
DOCUMENTATION
Reporting & Documentation
WHAT IS CAPTURED
Baseline & beneficiary data
+
Installation records
+
Date-stamped photos & videos
Attendance & activity logs
+
Beneficiary feedback
+
Financial records
=
WHAT IS PRODUCED
Project Documentation & Reports
Project dashboard (milestones & issues)
Monthly progress reports
Quarterly reports
Financial documentation
Success stories & case studies
Impact assessment report
Final project dossier
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
12
Notes: Everything gathered in the field — baseline data, installation records, photos and videos, training logs, feedback and financial records — is compiled into regular monthly and quarterly reports, case studies, an impact assessment and a final project dossier.

## Slide 13
SUSTAINABILITY
What Happens After Installation
Installation
System installed, tested & verified at each school
Ownership
Hardware handed over to school authorities
With documentation & training
Capacity Building
Teachers & local staff trained to operate and maintain
Maintenance
12-month maintenance support
12-month water-quality testing
Local technicians for check-ups & repairs
Long-Term Use
Periodic visits & usage monitoring
Community-led minor upkeep
Hardware life of 15–20 years
END STATE
The school owns and operates the system, backed by trained staff, local technicians and an engaged community.
INAUGURATION
MAINTENANCE
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
13
Notes: This slide answers what happens after the installers leave. The school owns the system, trained staff and local personnel run it, 12 months of maintenance and water-quality testing support its operation, and periodic visits, usage monitoring and community involvement keep it in use. The two photo frames are for the inauguration or handover and for maintenance visits.

## Slide 14
OUTCOMES & FIELD EXPERIENCE
Expected Impact & Past Projects
A · EXPECTED IMPACT
Health
Safe drinking water · Fewer cases of fluorosis, diarrhoea & waterborne illness · Better hygiene · Improved attendance
Community
Community ownership & involvement · Capacity building · Jobs for local technicians & trainers
Environment
Renewable solar energy · Low operational costs · Long-lasting, sustainable infrastructure
Measured by: baseline vs. endline data, surveys, on-site inspections and observation of hygiene practices
B · PAST PROJECTS & FIELD EXPERIENCE
Solar-Based RO Drinking Water Initiative · DigiGaon Foundation
14
Notes: Left: the outcomes the project expects in health, community and environment. Right: photographs from DigiGaon Foundation's previous field work.